Planning Meeting

For Tacoma Council PTA’s 100 year celebration

April 28, 2010 * Mandolin Café, Tacoma

Attendance:

Janet Stewart

Gladys Kendrick

Dan Voelpel, Tacoma Schools

Stacy Flores, Tacoma Schools

Susan Kunkel

Kris Anderson

Laura Burress

Joanne Cook

Marilyn Beale

- Discussed location of event with concerns about using Lincoln High when Lincoln Center students may still be in the building.  Also discussed weeknight versus weekend and all related pros/cons.  Staying with our Lincoln High School selection with request for early access to the areas of the building we need and to make it possible for elderly members of the public to visit and leave before it gets dark.

- Reception will be in Cafeteria.  Move to Auditorium for program.

- Budget:  $500 as determined by Tacoma Council PTA

- Possible conflicts – Stacy Flores will follow up on possible events that might bump into it.  Already noted that it is the Thursday before a 4-day weekend.  Plan to heavily publicize the date in advance (February 17, 2011) so that people may plan their long weekends around it.

- Resources to take advantage of:  a) Brian Cayman of the Northwest Room, Main Library, b) Mailing list for Golden Acorn/Annual Banquet.

- Dan Voelpel agreed to talk to Kathleen Merriman about promoting the event, especially to locate former PTA people and to increase awareness of event (and put on calendars).

- Created groups/duties:

  - Food/Refreshments

  - Communications/Publicity

  - Archives/Scrapbooks

  - Program (creating for presentation, displays, entertainment, Abby Hill)

  - Set-up/Decorations

  - Invitations

- While not obligated to sign up for groups, some people have already signed on:

Communications/Publicity                  Kim, Dan and Stacy

Archives/Scrapbooks                           Laura

Set-Up/Decorations                             Gladys

Invitations                                            Joanne, Susan K., Janet

Program                                               Kim, Kris

9)  Question for Nancy Pawlicki:   Whatever happened to the Brass Statue, the copy of the one in Pt. Defiance Park?  There was a slide show of how the statue was made.

- 100 year event will require people who have access to the building and are early enough to set up everything.  Have a 30 minute presentation first.  Kris suggested a video of people whose faces we could show as we announce they are in the room.  However, it would involve knowing who is going to be there “in advance.”

Individual PTA units will be encouraged to create and set up their own tables.  Council will have its table(s).  The agenda of the event should be printed on the event invitation.    Coffee is not a good idea for an event this time of day.

Kris Anderson will work on Abby Hill display.

- Tentative set up time is 4:30pm with doors opening at 6:00pm.  However, it may

be necessary to make displays available to older visitors who want/need to leave

before dark.]

Program ideas we are working with:   A video program, interviews with past council presidents, PTA members, former superintendents, etcetera.  Drama students might be able to create a play/performance based upon old Founders Day script (using updated information).

Action Item:  Kim to complete Building Use form. Patti DeRusha will need to sign this, and then it will be submitted to Lincoln/TPS.

NEXT MEETING:  June 23, 2010 (a Wednesday).  Time and place yet to be determined.

Kim Golding

(253) 906-8827

kg@nventure.com