Cultural Diversity and Inclusivity Plan Template

State:	Washington

| Task | Assigned To | Timeline | Status /comments |
| --- | --- | --- | --- |
| Assemble State Team | State President | July 2009 | A state team was assembled in July 2009. Each region has a representative on the team. Outreach Director was appointed by the State Board in Late May 2010. |
| Review National PTA strategic plan and materials on cultural inclusion and diversity (including definitions). | State Team | October or November 2009 | The National PTA materials including the National PTA policy and job description on cultural inclusion were reviewed with the State team. |
| Gather information on past State diversity and inclusion efforts | State Team | Annually review September | This is an ongoing process. The members of the State team represent a cross section of the diversity of Washington State. They are providing information on those diverse people living in their regions as well as information on who is missing from the discussion. |
| Review and evaluate current policy | State Team | September 2010 | The State team reviewed the National PTA plan and proposed adoption of State policy at the Board meeting in January 2010. |
| Obtain census data regarding state demographics and the demographics of locales within the state (demographics need to reflect specific areas, i.e. County/Region/District, in addition to the state as a whole.) | State Team | Annual Review Beginning of school year and end of school year School year 2011-2012 | 7 Regional Outreach Chairs and 9 EMLC representatives are meeting on a quarterly basis, providing input and data on their specific region. Gathering Ethnicity data we will work with Membership and hope to add a line in the membership form and envelopes. |
| Compile resources (within/outside of PTA) that will be used to ensure state/region/district/county councils reflect the diversity of the population (? Ethnicity, levels of income, programs example Sped ILC ELL) Statewide Community Organizations Educational Institutions Multicultural Organizations Parent Information Resource Center (PIRC) Philanthropic Organizations County/Region/District/Council Community Organizations Educational Institutions Multicultural Organizations Philanthropic Organizations | State Team County/ Region PTA Leaders | 2011 Start gathering during this year 2010-2011 October 2010 | We will try to gathering the within PTA data. ROCs will try to locate the data needed for the outside of PTA. Using City Office and Library resources. |
| Determine how non-traditional leaders will be identified | State Team | Recommended review September | ROCs And Region Director is going to encourage Those leaders to participate in the 2nd Annual EMLC. |
| Establish a State Advisory Board consisting of five-seven past State leaders from across the state whose term shall be concurrent with the appointing president; To meet at least bi-annually To identify potential leaders To serve as mentors To report at State Board meetings on activities | State President | September 2010 | The Outreach Committee provides this function. |
| Ensure that state leaders and ROCs complete the National PTA E-Learning Cultural Competency Course | State Team | October 2010 reviewed Annually | Individuals be required to present certification of completion to State Board We currently have a total of 42 members that have completed the course on line or at PTA Conferences (we created a certificate which participants will receive in the mail after the conference.) |
| Encourage the utilization of EMLC participants in leadership roles across all levels of the organization | State Team | Annually | We currently have a couple in different leadership roles. |
| Plan Components |  |  |  |
| Background on state and diversity and inclusion efforts. Demographic information. State desired outcome/goal Commitment statement by state leaders Statement regarding diversity/inclusivity in individual and committee plans of work Resource utilization Training requirements Assessment procedure County/Region/District/Council Procedures/Accountability Local Unit Procedures/Accountability Follow-up Conclusion |  | Work done in 2011 |  |
| Submit completed plan to National PTA, Membership and Field Services Department | State President | DUE December 15, Annually |  |